## Slide 1
HARBOR DESK / PRODUCT BETA REVIEW
Context
Synthetic meeting · 2026-02-03 · OpxSkills practice
01
1
CSV reporting feature
The team is preparing a beta release.
TARGET LAUNCH
2026-02-16
Conditional on completion of
accessibility checks.
Not an approved launch commitment.
Notes: Source: meeting-notes.txt; [1] Context. [1] Context The team is preparing a beta release of a CSV reporting feature. Target launch date: 2026-02-16, conditional on the accessibility checks being completed. This is a target date, not an approved launch commitment. This source is synthetic practice material. No additional approvals, owners, forecasts, or charts have been introduced.

## Slide 2
HARBOR DESK / PRODUCT BETA REVIEW
Decisions
Synthetic meeting · 2026-02-03 · OpxSkills practice
02
20
existing customers
in the beta
CONFIRMED SCOPE
2
Scheduled exports stay out
Keep automated scheduled exports
outside the beta scope.
3
No scope expansion
Do not expand beta scope
at this checkpoint.
Notes: Source: meeting-notes.txt; [2] Confirmed decisions. [2] Confirmed decisions Limit the beta to 20 existing customers. Keep automated scheduled exports outside the beta scope. Do not expand beta scope at this checkpoint. This source is synthetic practice material. No additional approvals, owners, forecasts, or charts have been introduced.

## Slide 3
HARBOR DESK / PRODUCT BETA REVIEW
Open risks
Synthetic meeting · 2026-02-03 · OpxSkills practice
03
1
Accessibility
Keyboard navigation in the export dialog has not completed accessibility review.
2
Missing CSV rows
CSV export drops rows with an empty optional comment field.
3
Support training
A training session is needed.
Owner: unassigned
Due date: unassigned
No revenue forecast or adoption projection was supplied.
Notes: Source: meeting-notes.txt; [3] Open risks and questions. [3] Open risks and questions Keyboard navigation in the export dialog has not completed accessibility review. The CSV export currently drops rows with an empty optional comment field. Support staff will need a training session, but no owner or due date has been assigned. There is no revenue forecast or adoption projection in this meeting record. This source is synthetic practice material. No additional approvals, owners, forecasts, or charts have been introduced.

## Slide 4
HARBOR DESK / PRODUCT BETA REVIEW
Action owners
Synthetic meeting · 2026-02-03 · OpxSkills practice
04
OWNER
ACTION
DUE DATE
Maya
Fix the missing-row CSV export bug.
2026-02-06
Leo
Complete the export-dialog
accessibility checks.
2026-02-09
Unassigned
Arrange support training.
Unassigned
Notes: Source: meeting-notes.txt; [4] Actions. [4] Actions Maya: fix the missing-row CSV export bug by 2026-02-06. Leo: complete the export-dialog accessibility checks by 2026-02-09. Unassigned: arrange support training. Due date unassigned. This source is synthetic practice material. No additional approvals, owners, forecasts, or charts have been introduced.

## Slide 5
HARBOR DESK / PRODUCT BETA REVIEW
Next checkpoint
Synthetic meeting · 2026-02-03 · OpxSkills practice
05
NEXT REVIEW
2026-02-10
Review findings before
confirming a launch date.
1
Review Maya’s regression results
2
Review Leo’s accessibility findings
2026-02-16 remains a conditional target,
not an approved launch commitment.
Notes: Source: meeting-notes.txt; [5] Next checkpoint; [4] Actions; [1] Context. [5] Next checkpoint The next review is on 2026-02-10. Review Maya's regression results and Leo's accessibility findings before confirming a launch date. [4] Actions Maya: fix the missing-row CSV export bug by 2026-02-06. Leo: complete the export-dialog accessibility checks by 2026-02-09. Unassigned: arrange support training. Due date unassigned. [1] Context The team is preparing a beta release of a CSV reporting feature. Target launch date: 2026-02-16, conditional on the accessibility checks being completed. This is a target date, not an approved launch commitment. This source is synthetic practice material. No additional approvals, owners, forecasts, or charts have been introduced.